## Sheet1
Stand-up Sequence | Action | Group | Cluster | Role | Existing Hostname (x.ltc.bcit.ca) | New/Interim Hostname (x.ltc.bcit.ca) | Goal Hostname (x.ltc.bcit.ca) | IP 142.232.x | Compute Cluster | vCPU's | RAM (Gb) | Requested Disk Type | Disk Driver | Disk1 Provisioning Type | Disk1 Size (Gb) | Disk2 Provisioning Type | Disk2 Size (Gb)
1 | Brand New | new | prod | control plane |  | prod-manager5 | prod-manager5 | .76.248 | BBY | 4 | 12 | SAS | VMWare paravirtual | Thin provision | 100
2 | Brand New | new | etcd | etcd |  | prod-etcd-consul-4 | prod-etcd4 | .76.37 | BBY | 4 | 8 | SSD | VMWare paravirtual | Thick provision eager zeroed | 100
3 | Brand New | new | dev | control plane, worker |  | dev-manager1 | dev-manager1 | .76.249 | BBY | 4 | 12 | SAS | VMWare paravirtual | Thin provision | 100 | Thick provision eager zeroed | 400
4 | Brand New | new | staging | control plane, worker |  | stage-manager1 | stage-manager1 | .76.38 | BBY | 4 | 12 | SAS | VMWare paravirtual | Thin provision | 100 | Thick provision eager zeroed | 400
5 | Update | legacy | - | load balancer | prod5 | prod-gate2 | prod-gate2 | .76.35 | BBY | 4 | 12 | SAS | VMWare paravirtual | Thin provision | 100
6 | Brand New | new | - | vault |  | vault | vault | .76.63 | BBY | 4 | 12 | SAS | VMWare paravirtual | Thin provision | 100
7 | Pause for verification | - | - |  | - | - | - | - | -
8 | New (Reprovision) | new | etcd | etcd | prod-etcd1 | prod-etcd-consul-1 | prod-etcd1 | .76.189 | BBY | 4 | 8 | SSD | VMWare paravirtual | Thick provision eager zeroed | 100
9 | New (Reprovision) | new | etcd | etcd | prod-etcd3 | prod-etcd-consul-3 | prod-etcd3 | .76.198 | BBY | 4 | 8 | SSD | VMWare paravirtual | Thick provision eager zeroed | 100
10 | New (Reprovision) | new | admin | rancher | prod-admin2 | prod-admin2 | prod-admin2 | .76.194 | BBY | 4 | 12 | SSD | VMWare paravirtual | Thin provision | 100
11 | New (Reprovision) | new | prod | control plane | prod-worker1 | prod-manager6 | prod-manager6 | .76.69 | BBY | 4 | 12 | SAS | VMWare paravirtual | Thin provision | 100
12 | New (Reprovision) | new | prod | worker | prod-worker9 | prod-worker11 | prod-worker11 | .76.199 | BBY | 4 | 12 | SAS | VMWare paravirtual | Thin provision | 100 | Thick provision eager zeroed | 400
13 | New (Reprovision) | new | staging | control plane, worker | prod-etcd2 | nomad-1 | stage-manager2 | .110.53 | DTC | 4 | 12 | SAS | VMWare paravirtual | Thin provision | 100 | Thick provision eager zeroed | 400
14 | New (Reprovision) | new | prod | worker | prod-worker4 | prod-worker10 | prod-worker10 | .76.46 | BBY | 4 | 12 | SAS | VMWare paravirtual | Thin provision | 100 | Thick provision eager zeroed | 400
15 | New (Reprovision) | legacy | staging | control plane | prod-manager1 | prod-manager7 | prod-manager7 | .76.40 | BBY | 4 | 12 | SAS | VMWare paravirtual | Thin provision | 100
16 | Pause for workload migration | - | - |  | - | - | - | - | -
17 | New (Reprovision) | new | staging | worker | prod-worker2 | prod-worker2 | stage-worker1 | .76.62 | BBY | 4 | 12 | SAS | VMWare paravirtual | Thin provision | 100 | Thick provision eager zeroed | 400
18 | Update | legacy | prod | rancher | prod-admin1 | prod-admin1 | prod-admin3 | .110.51 | DTC | 4 | 12 | SSD | VMWare paravirtual | Thin provision | 100
19 | - no change | legacy | prod | control plane, worker | prod-manager2 | prod-manager2 | dev-manager2 | .110.50 | DTC | 4 | 12 | SAS | VMWare paravirtual | Thin provision | 100 | Thick provision eager zeroed | 400
20 | - no change | legacy | prod | control plane, worker | prod-manager3 | prod-manager3 | dev-manager3 | .76.153 | BBY | 4 | 12 | SAS | VMWare paravirtual | Thin provision | 100 | Thick provision eager zeroed | 400
21 | - no change | legacy | prod | control plane, worker | prod-manager4 | prod-manager4 | stage-manager3 | .76.47 | BBY | 4 | 12 | SAS | VMWare paravirtual | Thin provision | 100 | Thick provision eager zeroed | 400
22 | - no change | legacy | prod | worker | prod-worker3 | prod-worker3 | prod-worker7 | .110.52 | DTC | 4 | 12 | SAS | VMWare paravirtual | Thin provision | 100 | Thick provision eager zeroed | 400
23 | Update | legacy | prod | worker | prod-gate1 | prod-gate1 | prod-worker5 | .76.186 | BBY | 4 | 12 | SAS | VMWare paravirtual | Thin provision | 100 | Thick provision eager zeroed | 400
24 | - no change | legacy | - | load balancer | prod4 | prod4 | prod-gate3 | .76.41 | BBY | 4 | 12 | SAS | VMWare paravirtual | Thin provision | 100
25 | - no change | legacy | - | - | test1 |  | testing1 | .76.51 | BBY | 4 | 12 | SAS | VMWare paravirtual | Thin provision | 100 | Thick provision eager zeroed | 400
26 | - no change | legacy | - | - | prod1 | prod1 | - | .76.65 | BBY | 4 | 12 | SAS | VMWare paravirtual | Thin provision | 100 | Thick provision eager zeroed | 400
[14 empty] | Root disk total (Gb) | 2400 | Secondary disk total (Gb) | 5200
LEGEND
complete
hostname change